## Data (hidden)
Timeline start | 2016-11-01
timeline end | 2017-05-20
| First Completion | 2017-03-08
| Last Completion | 2017-05-20 |  | 73
Sprint Start Dates | 2016-11-01 | 2016-11-15 | 2016-11-29 | 2016-12-13 | 2016-12-27 | 2017-01-10 | 2017-01-24 | 2017-02-07 | 2017-02-21 | 2017-03-07 | 2017-03-21 | 2017-04-04 | 2017-04-18 | 2017-05-02 | 2017-05-16 | 2017-05-30 | 2017-06-13 | 2017-06-27 | 2017-07-11 | 2017-07-25 | 2017-08-08 | 2017-08-22 | 2017-09-05 | 2017-09-19 | 2017-10-03
| 2016-11-01: Min Wait Time; 2016-11-15: 0; 2017-01-10: 0; 2017-03-07: 0; 2017-05-02: 0; 2017-06-27: 0; 2017-08-22: 5 | 5 |  |  |  | 10 |  |  |  | 10
| 2016-11-01: Max Wait Time; 2016-11-15: 10; 2017-01-10: 10; 2017-03-07: 5; 2017-05-02: 5; 2017-06-27: 5; 2017-08-22: 15 | 15 |  |  |  | 20 |  |  |  | 20
| 2016-11-01: Min Task Time; 2016-11-29: 10; 2017-01-24: 10; 2017-03-21: 10; 2017-05-16: 0; 2017-07-11: 5; 2017-09-05: 10 |  | 5 |  |  |  | 10 |  |  |  | 1
| 2016-11-01: Max Task Time; 2016-11-29: 30; 2017-01-24: 20; 2017-03-21: 20; 2017-05-16: 5; 2017-07-11: 10; 2017-09-05: 20 |  | 10 |  |  |  | 20 |  |  |  | 2
Level 3
| 2016-11-15: Requirement phase; 2017-01-10: Design, Coding & Unit Testing phase; 2017-03-07: Deploy to Dev Integration Env phase; 2017-05-02: SCA, Dev Integration Tests, Coverage, TD Assessment phase; 2017-06-27: Deploy to QA Env phase; 2017-08-22: Functional Testing and Regression phase | Deploy to NFR Testing Env(Performance and Security) phase |  |  |  | Run NFR Tests(Performance and Security) phase |  |  |  | Deploy to Production phase
Product Name | Work Item | Task Start Time | Task End Time | Task Time | Wait time | Task Start Time | Task End Time | Task Time | Wait time | Task Start Time | Task End Time | Task Time | Wait time | Task Start Time | Task End Time | Task Time | Wait time | Task Start Time | Task End Time | Task Time | Wait time | Task Start Time | Task End Time | Task Time | Wait time | Task Start Time | Task End Time | Task Time | Wait time | Task Start Time | Task End Time | Task Time | Wait time | Task Start Time | Task End Time | Task Time | Wait time
Product 1 | Story 1 | 2016-11-09 | 2016-11-22 | 13 | 8 | 2016-11-26 | 2016-12-09 | 13 | 4 | 2016-12-12 | 2016-12-30 | 18 | 3 | 2017-01-04 | 2017-01-04 | 0 | 5 | 2017-01-04 | 2017-01-14 | 10 | 0 | 2017-01-21 | 2017-02-10 | 20 | 7 | 2017-02-19 | 2017-02-24 | 5 | 9 | 2017-03-06 | 2017-03-25 | 19 | 10 | 2017-04-08 | 2017-04-10 | 2 | 14
Product 1 | Story 2 | 2016-11-11 | 2016-12-02 | 21 | 10 | 2016-12-12 | 2016-12-22 | 10 | 10 | 2016-12-27 | 2017-01-14 | 18 | 5 | 2017-01-15 | 2017-01-17 | 2 | 1 | 2017-01-17 | 2017-01-25 | 8 | 0 | 2017-02-05 | 2017-02-20 | 15 | 11 | 2017-03-02 | 2017-03-07 | 5 | 10 | 2017-03-25 | 2017-04-13 | 19 | 18 | 2017-04-26 | 2017-04-27 | 1 | 13
Product 1 | Story 1 | 2016-11-11 | 2016-12-09 | 28 | 10 | 2016-12-11 | 2016-12-28 | 17 | 2 | 2016-12-31 | 2017-01-11 | 11 | 3 | 2017-01-16 | 2017-01-19 | 3 | 5 | 2017-01-20 | 2017-01-30 | 10 | 1 | 2017-02-12 | 2017-03-03 | 19 | 13 | 2017-03-16 | 2017-03-23 | 7 | 13 | 2017-04-11 | 2017-05-01 | 20 | 19 | 2017-05-19 | 2017-05-20 | 1 | 18
Product 1 | Story 3 | 2016-11-07 | 2016-11-18 | 11 | 6 | 2016-11-26 | 2016-12-10 | 14 | 8 | 2016-12-10 | 2016-12-23 | 13 | 0 | 2016-12-26 | 2016-12-27 | 1 | 3 | 2016-12-30 | 2017-01-06 | 7 | 3 | 2017-01-14 | 2017-01-30 | 16 | 8 | 2017-02-06 | 2017-02-15 | 9 | 7 | 2017-02-27 | 2017-03-16 | 17 | 12 | 2017-04-02 | 2017-04-04 | 2 | 17
Product 2 | Story 4 | 2016-11-10 | 2016-12-03 | 23 | 9 | 2016-12-12 | 2016-12-26 | 14 | 9 | 2016-12-26 | 2017-01-07 | 12 | 0 | 2017-01-08 | 2017-01-11 | 3 | 1 | 2017-01-13 | 2017-01-21 | 8 | 2 | 2017-02-05 | 2017-02-17 | 12 | 15 | 2017-02-24 | 2017-03-03 | 7 | 7 | 2017-03-17 | 2017-03-30 | 13 | 14 | 2017-04-19 | 2017-04-20 | 1 | 20
Product 2 | Story 5 | 2016-11-02 | 2016-11-13 | 11 | 1 | 2016-11-20 | 2016-11-30 | 10 | 7 | 2016-11-30 | 2016-12-12 | 12 | 0 | 2016-12-16 | 2016-12-20 | 4 | 4 | 2016-12-20 | 2016-12-25 | 5 | 0 | 2017-01-07 | 2017-01-18 | 11 | 13 | 2017-01-26 | 2017-02-02 | 7 | 8 | 2017-02-14 | 2017-02-25 | 11 | 12 | 2017-03-07 | 2017-03-08 | 1 | 10
Level 2
| 2016-11-15: 2017-03-08; 2017-03-07: Sprint: Current -3; 2017-04-04: 2017-03-22; 2017-07-25: Sprint: Current -2; 2017-08-22: 2017-04-05 |  |  |  |  | Sprint: Current -1 |  | 2017-04-19 | [7 empty] | Sprint: Current
|  | Velocity | Deployment/ sprint | LoC changed/ sprint | Lead Time | Average deployment time | Failed Deployment / sprint | Ticket Volume | Technical Debt (TD) | # of items on Hold |  | Velocity | Deployment/ sprint | LoC changed/ sprint | Lead Time | Average deployment time | Failed Deployment / sprint | Ticket Volume | Technical Debt (TD) | # of items on Hold |  | Velocity | Deployment/ sprint | LoC changed/ sprint | Lead Time | Average deployment time | Failed Deployment / sprint | Ticket Volume | Technical Debt (TD) | # of items on Hold |  | Velocity | Deployment/ sprint | LoC changed/ sprint | Lead Time | Average deployment time | Failed Deployment / sprint | Ticket Volume | Technical Debt (TD) | # of items on Hold
| Product 1 | 21 | 14 | 292 | 194 | 7.9375 | 2 | 29 | 79 | 2 |  | 33 | 18 | 332 | 194 | 7.9375 | 3 | 33 | 80 | 3 |  | 31 | 10 | 285 | 194 | 7.9375 | 2 | 29 | 76 | 3 |  | 20 | 17 | 224 | 194 | 7.9375 | 3 | 22 | 89 | 2
| Product 2 | 29 | 18 | 152 | 169 | 6.625 | 3 | 15 | 62 | 3 |  | 34 | 11 | 282 | 169 | 6.625 | 2 | 28 | 60 | 3 |  | 36 | 14 | 342 | 169 | 6.625 | 2 | 34 | 57 | 4 |  | 38 | 13 | 351 | 169 | 6.625 | 2 | 35 | 73 | 4
|  | JIRA - Story Point | Jenkin - number of builds | Git - Hub | Calculated | Calculated | Jenkin | JIRA - number of bugs | Sonar - value | JIRA - open tasks and story
Level 1 | bar: 2017-06-13
| 2016-11-15: 2017-03-08; 2016-12-27: Sprint: Current -3; 2017-04-04: 2017-03-22; 2017-05-16: Sprint: Current -2; 2017-08-22: 2017-04-05; 2017-10-03: Sprint: Current -1 | [6 empty] | 2017-04-19 |  |  | Sprint: Current
| 2016-11-15: Lead Time; 2016-11-29: Ticket Volume; 2016-12-13: Technical Debt (TD); 2016-12-27: # of items on Hold; 2017-04-04: Lead Time; 2017-04-18: Ticket Volume; 2017-05-02: Technical Debt (TD); 2017-05-16: # of items on Hold; 2017-08-22: Lead Time; 2017-09-05: Ticket Volume; 2017-09-19: Technical Debt (TD); 2017-10-03: # of items on Hold | [6 empty] | Lead Time | Ticket Volume | Technical Debt (TD) | # of items on Hold
| 2016-11-01: Product 1; 2016-11-15: 194; 2016-11-29: 29; 2016-12-13: 79; 2016-12-27: 2; 2017-04-04: 194; 2017-04-18: 33; 2017-05-02: 80; 2017-05-16: 3; 2017-08-22: 194; 2017-09-05: 29; 2017-09-19: 76; 2017-10-03: 3 | [6 empty] | 194 | 22 | 89 | 2
| 2016-11-01: Product 2; 2016-11-15: 169; 2016-11-29: 15; 2016-12-13: 62; 2016-12-27: 3; 2017-04-04: 169; 2017-04-18: 28; 2017-05-02: 60; 2017-05-16: 3; 2017-08-22: 169; 2017-09-05: 34; 2017-09-19: 57; 2017-10-03: 4 | [6 empty] | 169 | 35 | 73 | 4
Formulas:
Task Start Time = [Task End Time]+RANDBETWEEN(AA8,AA9)
Task Start Time = [Task End Time]+RANDBETWEEN(AE8,AE9)
Task End Time = [Task Start Time]+RANDBETWEEN(AB11,AB12)
Task End Time = [Task Start Time]+RANDBETWEEN(AF11,AF12)
Task Time = [Task Start Time]+14

## Level 3
|  | Requirement phase |  | Design, Coding and Unit Testing |  | Deploy to Dev Integration Env |  | SCA, Dev Integration Tests, Coverage, TD Assessment |  | Deploy to QA Env |  | Functional Testing |  | Deploy to NFR Testing Env |  | Run NFR Tests |  | Prod Toll Gate |  | Deploy to Production
Row Labels | Average of 1_Wait Time | Average of 1_Task Time | Average of 2_Wait Time | Average of 2_Task Time | Average of 3_Wait Time | Average of 3_Task Time | Average of 4_Wait Time | Average of 4_Task Time | Average of 5_Task Time | Average of 5_Wait Time | Average of 6_Wait Time | Average of 6_Task Time | Average of 7_Wait Time | Average of 7_Task Time | Average of 8_Wait Time | Average of 8_Task Time | Average of 9_Wait Time | Average of 9_Task Time | Average of 10_Wait Time | Average of 10_Task Time | Average of Lead Time
Product 5 | 2 | 13.8667 | 1.6667 | 19.6 | 0 | 1.4 | 0.93333 | 2.9333 | 0.93333 | 0.73333 | 0.066667 | 21.1333 | 1.2 | 3.9333 | 2.5333 | 8.6667 | 2.5333 | 1.8 | 2.5333 | 2.4667 | 88.9333
Story 1 | 2 | 14 | 1 | 18 | 0 | 1 | 0 | 3 | 1 | 1 | 1 | 17 | 1 | 4 | 3 | 9 | 3 | 2 | 5 | 5 | 89
Story 2 | 1 | 9 | 1 | 22 | 0 | 1 | 1 | 4 | 0 | 1 | 0 | 25 | 1 | 5 | 4 | 8 | 2 | 1 | 4 | 1 | 90
Story 3 | 2 | 15 | 3 | 25 | 0 | 2 | 2 | 5 | 1 | 2 | 0 | 15 | 2 | 6 | 3 | 7 | 3 | 2 | 3 | 2 | 98
Story 4 | 4 | 13 | 2 | 17 | 0 | 1 | 0 | 2 | 1 | 1 | 0 | 28 | 1 | 3 | 2 | 10 | 1 | 1 | 2 | 3 | 88
Story 5 | 2 | 16 | 1 | 16 | 0 | 1 | 0 | 3 | 2 | 0 | 0 | 18 | 3 | 2 | 3 | 11 | 4 | 1 | 1 | 4 | 86
Story 6 | 4 | 10 | 2 | 23 | 0 | 2 | 3 | 1 | 0 | 0 | 0 | 25 | 1 | 4 | 2 | 7 | 2 | 2 | 3 | 3 | 90
Story 7 | 2 | 13 | 3 | 21 | 0 | 1 | 0 | 3 | 3 | 2 | 0 | 20 | 2 | 3 | 3 | 8 | 1 | 1 | 2 | 2 | 88
Story 8 | 1 | 16 | 1 | 20 | 0 | 2 | 2 | 4 | 1 | 0 | 0 | 22 | 1 | 5 | 1 | 12 | 3 | 1 | 4 | 2 | 97
Story 9 | 3 | 13 | 2 | 19 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 21 | 0 | 3 | 2 | 9 | 2 | 1 | 2 | 3 | 80
Story 10 | 2 | 14 | 0 | 18 | 0 | 2 | 2 | 3 | 1 | 0 | 0 | 25 | 0 | 2 | 4 | 6 | 3 | 3 | 3 | 1 | 87
Story 11 | 3 | 16 | 1 | 17 | 0 | 1 | 0 | 4 | 0 | 0 | 0 | 24 | 1 | 4 | 1 | 7 | 2 | 2 | 2 | 4 | 86
Story 12 | 1 | 12 | 2 | 20 | 0 | 2 | 2 | 2 | 1 | 2 | 0 | 19 | 2 | 6 | 3 | 8 | 3 | 4 | 1 | 2 | 91
Story 13 | 0 | 15 | 3 | 21 | 0 | 1 | 0 | 4 | 2 | 1 | 0 | 17 | 0 | 3 | 2 | 9 | 2 | 3 | 3 | 3 | 89
Story 14 | 2 | 17 | 2 | 19 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 20 | 2 | 4 | 3 | 9 | 3 | 2 | 2 | 1 | 89
Story 15 | 1 | 15 | 1 | 18 | 0 | 2 | 0 | 2 | 1 | 1 | 0 | 21 | 1 | 5 | 2 | 10 | 4 | 1 | 1 | 1 | 86
Product 6 | 1.9333 | 5.6667 | 1.6 | 10.4 | 0.33333 | 1.2667 | 0.53333 | 3.1333 | 1.2 | 1.4 | 0.6 | 8.9333 | 0.8 | 4.5333 | 2.4667 | 8.6667 | 2.8 | 2.9333 | 5 | 4.9333 | 67.2
Story 1 | 2 | 6 | 1 | 8 | 0 | 1 | 0 | 3 | 1 | 1 | 1 | 9 | 1 | 4 | 3 | 8 | 3 | 2 | 5 | 5 | 62
Story 2 | 2 | 5 | 2 | 10 | 0 | 2 | 0 | 3 | 1 | 1 | 0 | 8 | 0 | 5 | 2 | 9 | 2 | 1 | 4 | 6 | 61
Story 3 | 3 | 4 | 1 | 11 | 0 | 1 | 1 | 2 | 2 | 1 | 0 | 10 | 0 | 6 | 3 | 10 | 4 | 2 | 5 | 4 | 67
Story 4 | 2 | 6 | 2 | 11 | 1 | 1 | 0 | 4 | 1 | 1 | 2 | 11 | 1 | 3 | 1 | 11 | 2 | 3 | 5 | 3 | 69
Story 5 | 1 | 7 | 2 | 9 | 0 | 2 | 1 | 3 | 2 | 2 | 0 | 12 | 1 | 4 | 2 | 12 | 3 | 2 | 6 | 5 | 75
Story 6 | 2 | 8 | 2 | 10 | 1 | 1 | 0 | 2 | 1 | 1 | 1 | 10 | 1 | 5 | 3 | 8 | 2 | 4 | 4 | 4 | 68
Story 7 | 1 | 4 | 1 | 9 | 0 | 2 | 0 | 4 | 1 | 2 | 0 | 7 | 1 | 4 | 4 | 7 | 3 | 3 | 6 | 5 | 63
Story 8 | 2 | 5 | 2 | 12 | 1 | 1 | 1 | 3 | 1 | 1 | 0 | 8 | 1 | 6 | 1 | 9 | 2 | 5 | 5 | 7 | 71
Story 9 | 3 | 6 | 3 | 10 | 0 | 2 | 0 | 2 | 1 | 2 | 1 | 9 | 0 | 5 | 2 | 6 | 4 | 2 | 4 | 6 | 65
Story 10 | 2 | 4 | 2 | 10 | 1 | 1 | 0 | 3 | 1 | 1 | 0 | 10 | 1 | 4 | 3 | 7 | 5 | 3 | 6 | 5 | 67
Story 11 | 1 | 7 | 1 | 10 | 0 | 2 | 2 | 4 | 2 | 2 | 2 | 7 | 0 | 7 | 4 | 8 | 2 | 4 | 5 | 6 | 75
Story 12 | 2 | 8 | 2 | 11 | 0 | 1 | 0 | 3 | 1 | 1 | 1 | 6 | 2 | 4 | 2 | 9 | 1 | 3 | 4 | 4 | 63
Story 13 | 3 | 6 | 2 | 12 | 1 | 2 | 0 | 2 | 1 | 2 | 0 | 8 | 0 | 3 | 3 | 9 | 4 | 2 | 5 | 5 | 67
Story 14 | 2 | 5 | 1 | 12 | 0 | 0 | 2 | 4 | 1 | 1 | 0 | 9 | 2 | 4 | 4 | 10 | 2 | 3 | 6 | 4 | 70
Story 15 | 1 | 4 | 0 | 11 | 0 | 0 | 1 | 5 | 1 | 2 | 1 | 10 | 1 | 4 | 0 | 7 | 3 | 5 | 5 | 5 | 65
Product 4 | 3.3333 | 19.6667 | 2.3333 | 26.8333 | 2.75 | 3.4167 | 2.75 | 3.75 | 3.8333 | 2.9167 | 3.5 | 18.8333 | 2.25 | 4.25 | 4.4167 | 10.25 | 3.0833 | 2 | 3.9167 | 5.8333 | 126.5833
Story 1 | 3 | 33 | 2 | 25 | 2 | 1 | 3 | 1 | 2 | 3 | 2 | 13 | 3 | 2 | 7 | 9 | 5 | 1 | 5 | 3 | 122
Story 2 | 2 | 14 | 2 | 29 | 3 | 4 | 2 | 4 | 4 | 3 | 2 | 25 | 1 | 6 | 2 | 8 | 2 | 2 | 2 | 6 | 121
Story 3 | 5 | 13 | 3 | 25 | 5 | 5 | 2 | 7 | 5 | 4 | 4 | 21 | 2 | 5 | 3 | 10 | 3 | 3 | 5 | 10 | 135
Story 4 | 2 | 16 | 1 | 27 | 1 | 3 | 2 | 3 | 3 | 2 | 6 | 24 | 1 | 4 | 3 | 12 | 3 | 2 | 2 | 5 | 120
Story 5 | 3 | 15 | 3 | 25 | 4 | 4 | 2 | 5 | 4 | 4 | 3 | 15 | 2 | 3 | 5 | 12 | 3 | 1 | 4 | 7 | 121
Story 6 | 4 | 15 | 2 | 22 | 2 | 4 | 4 | 6 | 5 | 3 | 4 | 17 | 3 | 6 | 2 | 11 | 4 | 2 | 5 | 6 | 123
Story 7 | 5 | 12 | 4 | 30 | 3 | 7 | 3 | 5 | 7 | 2 | 5 | 19 | 4 | 5 | 3 | 13 | 2 | 3 | 3 | 4 | 134
Story 8 | 2 | 34 | 2 | 23 | 1 | 1 | 2 | 1 | 2 | 3 | 2 | 17 | 1 | 7 | 4 | 10 | 3 | 4 | 4 | 5 | 126
Story 9 | 3 | 16 | 3 | 28 | 3 | 3 | 5 | 2 | 3 | 4 | 4 | 22 | 2 | 3 | 7 | 7 | 5 | 2 | 6 | 6 | 131
Story 10 | 6 | 36 | 1 | 29 | 4 | 2 | 3 | 1 | 2 | 2 | 3 | 12 | 3 | 2 | 6 | 8 | 4 | 1 | 4 | 7 | 130
Story 11 | 2 | 17 | 3 | 28 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 20 | 3 | 5 | 5 | 12 | 2 | 2 | 4 | 5 | 121
Story 12 | 3 | 15 | 2 | 31 | 3 | 5 | 3 | 8 | 7 | 3 | 4 | 21 | 2 | 3 | 6 | 11 | 1 | 1 | 3 | 6 | 135

## Level3_Data
Product Name | Work Item | Start Date | Requirement | 1_Start Time | 1_End Time | 1_Task Time | 1_Wait Time | Design, Coding and Unit Testing | 2_Start Time | 2_End Time | 2_Task Time | 2_Wait Time | Deploy to Dev Integration Env | 3_Start Time | 3_End Time | 3_Task Time | 3_Wait Time | SCA, Dev Integration Tests, Coverage, TD Assessment | 4_Start Time | 4_End Time | 4_Task Time | 4_Wait Time | Deploy to QA Env | 5_Start Time | 5_End Time | 5_Task Time | 5_Wait Time | Functional Testing | 6_Start Time | k | 6_Task Time | 6_Wait Time | Deploy to NFR Testing Env | 7_Start Time | 7_End Time | 7_Task Time | 7_Wait Time | Run NFR Tests | 8_Start Time | 8_End Time | 8_Task Time | 8_Wait Time | Prod Toll Gate | 9_Start Time | 9_End Time | 9_Task Time | 9_Wait Time | Deploy to Production | 10_Start Time | 10_End Time | 10_Task Time | 10_Wait Time | Lead Time | Average Deployment Time | Reference Date | Sprint | Avg
Product 4 | Story 7 | 2017-05-27 | Requirement | 2017-06-01 | 2017-06-09 | 8 | 5 | DCUT | 2017-06-13 | 2017-06-22 | 9 | 4 | DeployDev | 2017-06-25 | 2017-07-02 | 7 | 3 | InegrationTest | 2017-07-05 | 2017-07-10 | 5 | 3 | DeployQA | 2017-07-12 | 2017-07-19 | 7 | 2 | FunctionTest | 2017-07-24 | 2017-08-12 | 19 | 5 | DeployNFR | 2017-08-16 | 2017-08-21 | 5 | 4 | TestNFR | 2017-08-24 | 2017-09-06 | 13 | 3 | TollGate | 2017-09-08 | 2017-09-11 | 3 | 2 | DeployProd | 2017-09-14 | 2017-09-18 | 4 | 3 | 109 | 5.75 | 2017-09-18 | Sprint 4
Product 4 | Story 3 | 2017-06-08 | Requirement | 2017-06-13 | 2017-06-20 | 7 | 5 | DCUT | 2017-06-23 | 2017-07-04 | 11 | 3 | DeployDev | 2017-07-09 | 2017-07-14 | 5 | 5 | InegrationTest | 2017-07-16 | 2017-07-23 | 7 | 2 | DeployQA | 2017-07-27 | 2017-08-01 | 5 | 4 | FunctionTest | 2017-08-05 | 2017-08-26 | 21 | 4 | DeployNFR | 2017-08-28 | 2017-09-02 | 5 | 2 | TestNFR | 2017-09-05 | 2017-09-15 | 10 | 3 | TollGate | 2017-09-18 | 2017-09-21 | 3 | 3 | DeployProd | 2017-09-26 | 2017-10-06 | 10 | 5 | 115 | 6.25 | 2017-10-06 | Sprint 4
Product 4 | Story 12 | 2017-06-21 | Requirement | 2017-06-24 | 2017-06-30 | 6 | 3 | DCUT | 2017-07-02 | 2017-07-13 | 11 | 2 | DeployDev | 2017-07-16 | 2017-07-21 | 5 | 3 | InegrationTest | 2017-07-24 | 2017-08-01 | 8 | 3 | DeployQA | 2017-08-04 | 2017-08-11 | 7 | 3 | FunctionTest | 2017-08-15 | 2017-09-05 | 21 | 4 | DeployNFR | 2017-09-07 | 2017-09-10 | 3 | 2 | TestNFR | 2017-09-16 | 2017-09-27 | 11 | 6 | TollGate | 2017-09-28 | 2017-09-29 | 1 | 1 | DeployProd | 2017-10-02 | 2017-10-08 | 6 | 3 | 106 | 5.25 | 2017-10-08 | Sprint 4
Product 4 | Story 6 | 2017-06-03 | Requirement | 2017-06-07 | 2017-06-15 | 8 | 4 | DCUT | 2017-06-17 | 2017-06-28 | 11 | 2 | DeployDev | 2017-06-30 | 2017-07-04 | 4 | 2 | InegrationTest | 2017-07-08 | 2017-07-14 | 6 | 4 | DeployQA | 2017-07-17 | 2017-07-22 | 5 | 3 | FunctionTest | 2017-07-26 | 2017-08-12 | 17 | 4 | DeployNFR | 2017-08-15 | 2017-08-21 | 6 | 3 | TestNFR | 2017-08-23 | 2017-09-03 | 11 | 2 | TollGate | 2017-09-07 | 2017-09-09 | 2 | 4 | DeployProd | 2017-09-14 | 2017-09-20 | 6 | 5 | 105 | 5.25 | 2017-09-20 | Sprint 3
Product 4 | Story 5 | 2017-06-16 | Requirement | 2017-06-19 | 2017-06-24 | 5 | 3 | DCUT | 2017-06-27 | 2017-07-07 | 10 | 3 | DeployDev | 2017-07-11 | 2017-07-15 | 4 | 4 | InegrationTest | 2017-07-17 | 2017-07-22 | 5 | 2 | DeployQA | 2017-07-26 | 2017-07-30 | 4 | 4 | FunctionTest | 2017-08-02 | 2017-08-17 | 15 | 3 | DeployNFR | 2017-08-19 | 2017-08-22 | 3 | 2 | TestNFR | 2017-08-27 | 2017-09-08 | 12 | 5 | TollGate | 2017-09-11 | 2017-09-12 | 1 | 3 | DeployProd | 2017-09-16 | 2017-09-23 | 7 | 4 | 96 | 4.5 | 2017-09-23 | Sprint 3
Product 4 | Story 4 | 2017-06-29 | Requirement | 2017-07-01 | 2017-07-07 | 6 | 2 | DCUT | 2017-07-08 | 2017-07-19 | 11 | 1 | DeployDev | 2017-07-20 | 2017-07-23 | 3 | 1 | InegrationTest | 2017-07-25 | 2017-07-28 | 3 | 2 | DeployQA | 2017-07-30 | 2017-08-02 | 3 | 2 | FunctionTest | 2017-08-08 | 2017-09-01 | 24 | 6 | DeployNFR | 2017-09-02 | 2017-09-06 | 4 | 1 | TestNFR | 2017-09-09 | 2017-09-21 | 12 | 3 | TollGate | 2017-09-24 | 2017-09-26 | 2 | 3 | DeployProd | 2017-09-28 | 2017-10-03 | 5 | 2 | 94 | 3.75 | 2017-10-03 | Sprint 2
Product 4 | Story 2 | 2017-07-15 | Requirement | 2017-07-17 | 2017-07-23 | 6 | 2 | DCUT | 2017-07-25 | 2017-08-04 | 10 | 2 | DeployDev | 2017-08-07 | 2017-08-11 | 4 | 3 | InegrationTest | 2017-08-13 | 2017-08-17 | 4 | 2 | DeployQA | 2017-08-20 | 2017-08-24 | 4 | 3 | FunctionTest | 2017-08-26 | 2017-09-20 | 25 | 2 | DeployNFR | 2017-09-21 | 2017-09-27 | 6 | 1 | TestNFR | 2017-09-29 | 2017-10-07 | 8 | 2 | TollGate | 2017-10-09 | 2017-10-11 | 2 | 2 | DeployProd | 2017-10-13 | 2017-10-19 | 6 | 2 | 94 | 5 | 2017-10-19 | Sprint 3
Product 4 | Story 1 | 2017-06-25 | Requirement | 2017-06-28 | 2017-07-23 | 25 | 3 | DCUT | 2017-07-25 | 2017-08-19 | 25 | 2 | DeployDev | 2017-08-21 | 2017-08-22 | 1 | 2 | InegrationTest | 2017-08-25 | 2017-08-26 | 1 | 3 | DeployQA | 2017-08-29 | 2017-08-31 | 2 | 3 | FunctionTest | 2017-09-02 | 2017-09-15 | 13 | 2 | DeployNFR | 2017-09-18 | 2017-09-20 | 2 | 3 | TestNFR | 2017-09-27 | 2017-10-06 | 9 | 7 | TollGate | 2017-10-11 | 2017-10-12 | 1 | 5 | DeployProd | 2017-10-17 | 2017-10-20 | 3 | 5 | 114 | 2 | 2017-10-20 | Sprint 1
Product 4 | Story 11 | 2017-07-19 | Requirement | 2017-07-21 | 2017-07-27 | 6 | 2 | DCUT | 2017-07-30 | 2017-08-11 | 12 | 3 | DeployDev | 2017-08-13 | 2017-08-15 | 2 | 2 | InegrationTest | 2017-08-17 | 2017-08-19 | 2 | 2 | DeployQA | 2017-08-21 | 2017-08-23 | 2 | 2 | FunctionTest | 2017-08-26 | 2017-09-15 | 20 | 3 | DeployNFR | 2017-09-18 | 2017-09-23 | 5 | 3 | TestNFR | 2017-09-28 | 2017-10-10 | 12 | 5 | TollGate | 2017-10-12 | 2017-10-14 | 2 | 2 | DeployProd | 2017-10-18 | 2017-10-23 | 5 | 4 | 94 | 3.5 | 2017-10-23 | Sprint 2
Product 4 | Story 10 | 2017-07-08 | Requirement | 2017-07-14 | 2017-08-02 | 19 | 6 | DCUT | 2017-08-03 | 2017-09-01 | 29 | 1 | DeployDev | 2017-09-05 | 2017-09-07 | 2 | 4 | InegrationTest | 2017-09-10 | 2017-09-11 | 1 | 3 | DeployQA | 2017-09-13 | 2017-09-15 | 2 | 2 | FunctionTest | 2017-09-18 | 2017-09-30 | 12 | 3 | DeployNFR | 2017-10-03 | 2017-10-05 | 2 | 3 | TestNFR | 2017-10-11 | 2017-10-19 | 8 | 6 | TollGate | 2017-10-23 | 2017-10-24 | 1 | 4 | DeployProd | 2017-10-28 | 2017-11-04 | 7 | 4 | 113 | 3.25 | 2017-11-04 | Sprint 1
Product 4 | Story 9 | 2017-07-23 | Requirement | 2017-07-26 | 2017-08-02 | 7 | 3 | DCUT | 2017-08-05 | 2017-08-14 | 9 | 3 | DeployDev | 2017-08-17 | 2017-08-20 | 3 | 3 | InegrationTest | 2017-08-25 | 2017-08-27 | 2 | 5 | DeployQA | 2017-08-31 | 2017-09-03 | 3 | 4 | FunctionTest | 2017-09-07 | 2017-09-29 | 22 | 4 | DeployNFR | 2017-10-01 | 2017-10-04 | 3 | 2 | TestNFR | 2017-10-11 | 2017-10-18 | 7 | 7 | TollGate | 2017-10-23 | 2017-10-25 | 2 | 5 | DeployProd | 2017-10-31 | 2017-11-06 | 6 | 6 | 103 | 3.75 | 2017-11-06 | Sprint 1
Product 4 | Story 8 | 2017-07-18 | Requirement | 2017-07-20 | 2017-08-09 | 20 | 2 | DCUT | 2017-08-11 | 2017-09-03 | 23 | 2 | DeployDev | 2017-09-04 | 2017-09-05 | 1 | 1 | InegrationTest | 2017-09-07 | 2017-09-08 | 1 | 2 | DeployQA | 2017-09-11 | 2017-09-13 | 2 | 3 | FunctionTest | 2017-09-15 | 2017-10-02 | 17 | 2 | DeployNFR | 2017-10-03 | 2017-10-10 | 7 | 1 | TestNFR | 2017-10-14 | 2017-10-24 | 10 | 4 | TollGate | 2017-10-27 | 2017-10-31 | 4 | 3 | DeployProd | 2017-11-04 | 2017-11-09 | 5 | 4 | 112 | 3.75 | 2017-11-09 | Sprint 1 | 109.3333
Product 5 | Story 12 | 2017-06-17 | Requirement | 2017-06-18 | 2017-06-26 | 8 | 1 | DCUT | 2017-06-28 | 2017-07-07 | 9 | 2 | DeployDev | 2017-07-07 | 2017-07-09 | 2 | 0 | InegrationTest | 2017-07-11 | 2017-07-13 | 2 | 2 | DeployQA | 2017-07-15 | 2017-07-16 | 1 | 2 | FunctionTest | 2017-07-16 | 2017-08-04 | 19 | 0 | DeployNFR | 2017-08-06 | 2017-08-12 | 6 | 2 | TestNFR | 2017-08-15 | 2017-08-23 | 8 | 3 | TollGate | 2017-08-26 | 2017-09-05 | 10 | 3 | DeployProd | 2017-09-06 | 2017-09-08 | 2 | 1 | 82 | 2.75 | 2017-09-08 | Sprint 5
Product 5 | Story 9 | 2017-06-15 | Requirement | 2017-06-18 | 2017-06-25 | 7 | 3 | DCUT | 2017-06-27 | 2017-07-08 | 11 | 2 | DeployDev | 2017-07-08 | 2017-07-09 | 1 | 0 | InegrationTest | 2017-07-09 | 2017-07-11 | 2 | 0 | DeployQA | 2017-07-11 | 2017-07-11 | 0 | 0 | FunctionTest | 2017-07-11 | 2017-08-01 | 21 | 0 | DeployNFR | 2017-08-01 | 2017-08-04 | 3 | 0 | TestNFR | 2017-08-06 | 2017-08-15 | 9 | 2 | TollGate | 2017-08-17 | 2017-08-29 | 12 | 2 | DeployProd | 2017-08-31 | 2017-09-03 | 3 | 2 | 77 | 1.75 | 2017-09-03 | Sprint 5
Product 5 | Story 15 | 2017-06-12 | Requirement | 2017-06-13 | 2017-06-19 | 6 | 1 | DCUT | 2017-06-20 | 2017-07-01 | 11 | 1 | DeployDev | 2017-07-01 | 2017-07-03 | 2 | 0 | InegrationTest | 2017-07-03 | 2017-07-05 | 2 | 0 | DeployQA | 2017-07-06 | 2017-07-07 | 1 | 1 | FunctionTest | 2017-07-07 | 2017-07-28 | 21 | 0 | DeployNFR | 2017-07-29 | 2017-08-03 | 5 | 1 | TestNFR | 2017-08-05 | 2017-08-18 | 13 | 2 | TollGate | 2017-08-22 | 2017-09-03 | 12 | 4 | DeployProd | 2017-09-04 | 2017-09-05 | 1 | 1 | 84 | 2.25 | 2017-09-05 | Sprint 5
Product 5 | Story 13 | 2017-07-04 | Requirement | 2017-07-04 | 2017-07-12 | 8 | 0 | DCUT | 2017-07-15 | 2017-07-26 | 11 | 3 | DeployDev | 2017-07-26 | 2017-07-27 | 1 | 0 | InegrationTest | 2017-07-27 | 2017-07-31 | 4 | 0 | DeployQA | 2017-08-01 | 2017-08-03 | 2 | 1 | FunctionTest | 2017-08-03 | 2017-08-20 | 17 | 0 | DeployNFR | 2017-08-20 | 2017-08-23 | 3 | 0 | TestNFR | 2017-08-25 | 2017-09-04 | 10 | 2 | TollGate | 2017-09-06 | 2017-09-17 | 11 | 2 | DeployProd | 2017-09-20 | 2017-09-23 | 3 | 3 | 81 | 2.25 | 2017-09-23 | Sprint 4
Product 5 | Story 3 | 2017-07-24 | Requirement | 2017-07-26 | 2017-07-31 | 5 | 2 | DCUT | 2017-08-03 | 2017-08-13 | 10 | 3 | DeployDev | 2017-08-13 | 2017-08-15 | 2 | 0 | InegrationTest | 2017-08-17 | 2017-08-22 | 5 | 2 | DeployQA | 2017-08-24 | 2017-08-25 | 1 | 2 | FunctionTest | 2017-08-25 | 2017-09-09 | 15 | 0 | DeployNFR | 2017-09-11 | 2017-09-17 | 6 | 2 | TestNFR | 2017-09-20 | 2017-10-01 | 11 | 3 | TollGate | 2017-10-04 | 2017-10-14 | 10 | 3 | DeployProd | 2017-10-17 | 2017-10-19 | 2 | 3 | 85 | 2.75 | 2017-10-19 | Sprint 4
Product 5 | Story 10 | 2017-06-27 | Requirement | 2017-06-29 | 2017-07-05 | 6 | 2 | DCUT | 2017-07-05 | 2017-07-15 | 10 | 0 | DeployDev | 2017-07-15 | 2017-07-17 | 2 | 0 | InegrationTest | 2017-07-19 | 2017-07-22 | 3 | 2 | DeployQA | 2017-07-22 | 2017-07-23 | 1 | 0 | FunctionTest | 2017-07-23 | 2017-08-17 | 25 | 0 | DeployNFR | 2017-08-17 | 2017-08-19 | 2 | 0 | TestNFR | 2017-08-23 | 2017-09-03 | 11 | 4 | TollGate | 2017-09-06 | 2017-09-16 | 10 | 3 | DeployProd | 2017-09-19 | 2017-09-20 | 1 | 3 | 83 | 1.5 | 2017-09-20 | Sprint 4
Product 5 | Story 11 | 2017-06-23 | Requirement | 2017-06-26 | 2017-07-02 | 6 | 3 | DCUT | 2017-07-03 | 2017-07-14 | 11 | 1 | DeployDev | 2017-07-14 | 2017-07-15 | 1 | 0 | InegrationTest | 2017-07-15 | 2017-07-19 | 4 | 0 | DeployQA | 2017-07-19 | 2017-07-19 | 0 | 0 | FunctionTest | 2017-07-19 | 2017-08-12 | 24 | 0 | DeployNFR | 2017-08-13 | 2017-08-17 | 4 | 1 | TestNFR | 2017-08-18 | 2017-08-30 | 12 | 1 | TollGate | 2017-09-01 | 2017-09-12 | 11 | 2 | DeployProd | 2017-09-14 | 2017-09-18 | 4 | 2 | 84 | 2.25 | 2017-09-18 | Sprint 3
Product 5 | Story 8 | 2017-07-12 | Requirement | 2017-07-13 | 2017-07-20 | 7 | 1 | DCUT | 2017-07-21 | 2017-07-30 | 9 | 1 | DeployDev | 2017-07-30 | 2017-08-01 | 2 | 0 | InegrationTest | 2017-08-03 | 2017-08-07 | 4 | 2 | DeployQA | 2017-08-07 | 2017-08-08 | 1 | 0 | FunctionTest | 2017-08-08 | 2017-08-30 | 22 | 0 | DeployNFR | 2017-08-31 | 2017-09-05 | 5 | 1 | TestNFR | 2017-09-06 | 2017-09-18 | 12 | 1 | TollGate | 2017-09-21 | 2017-09-30 | 9 | 3 | DeployProd | 2017-10-04 | 2017-10-06 | 2 | 4 | 85 | 2.5 | 2017-10-06 | Sprint 3
Product 5 | Story 14 | 2017-07-09 | Requirement | 2017-07-11 | 2017-07-17 | 6 | 2 | DCUT | 2017-07-19 | 2017-07-31 | 12 | 2 | DeployDev | 2017-07-31 | 2017-08-01 | 1 | 0 | InegrationTest | 2017-08-03 | 2017-08-05 | 2 | 2 | DeployQA | 2017-08-05 | 2017-08-05 | 0 | 0 | FunctionTest | 2017-08-05 | 2017-08-25 | 20 | 0 | DeployNFR | 2017-08-27 | 2017-08-31 | 4 | 2 | TestNFR | 2017-09-03 | 2017-09-15 | 12 | 3 | TollGate | 2017-09-18 | 2017-09-30 | 12 | 3 | DeployProd | 2017-10-02 | 2017-10-03 | 1 | 2 | 84 | 1.5 | 2017-10-03 | Sprint 3
Product 5 | Story 5 | 2017-07-18 | Requirement | 2017-07-20 | 2017-07-26 | 6 | 2 | DCUT | 2017-07-27 | 2017-08-07 | 11 | 1 | DeployDev | 2017-08-07 | 2017-08-08 | 1 | 0 | InegrationTest | 2017-08-08 | 2017-08-11 | 3 | 0 | DeployQA | 2017-08-11 | 2017-08-13 | 2 | 0 | FunctionTest | 2017-08-13 | 2017-08-31 | 18 | 0 | DeployNFR | 2017-09-03 | 2017-09-05 | 2 | 3 | TestNFR | 2017-09-08 | 2017-09-18 | 10 | 3 | TollGate | 2017-09-22 | 2017-10-03 | 11 | 4 | DeployProd | 2017-10-04 | 2017-10-08 | 4 | 1 | 80 | 2.25 | 2017-10-08 | Sprint 2
Product 5 | Story 1 | 2017-07-25 | Requirement | 2017-07-27 | 2017-08-03 | 7 | 2 | DCUT | 2017-08-04 | 2017-08-14 | 10 | 1 | DeployDev | 2017-08-14 | 2017-08-15 | 1 | 0 | InegrationTest | 2017-08-15 | 2017-08-18 | 3 | 0 | DeployQA | 2017-08-19 | 2017-08-20 | 1 | 1 | FunctionTest | 2017-08-21 | 2017-09-07 | 17 | 1 | DeployNFR | 2017-09-08 | 2017-09-12 | 4 | 1 | TestNFR | 2017-09-15 | 2017-09-27 | 12 | 3 | TollGate | 2017-09-30 | 2017-10-10 | 10 | 3 | DeployProd | 2017-10-15 | 2017-10-20 | 5 | 5 | 85 | 2.75 | 2017-10-20 | Sprint 2
Product 5 | Story 7 | 2017-07-31 | Requirement | 2017-08-02 | 2017-08-10 | 8 | 2 | DCUT | 2017-08-13 | 2017-08-23 | 10 | 3 | DeployDev | 2017-08-23 | 2017-08-24 | 1 | 0 | InegrationTest | 2017-08-24 | 2017-08-27 | 3 | 0 | DeployQA | 2017-08-29 | 2017-09-01 | 3 | 2 | FunctionTest | 2017-09-01 | 2017-09-21 | 20 | 0 | DeployNFR | 2017-09-23 | 2017-09-26 | 3 | 2 | TestNFR | 2017-09-29 | 2017-10-08 | 9 | 3 | TollGate | 2017-10-09 | 2017-10-19 | 10 | 1 | DeployProd | 2017-10-21 | 2017-10-23 | 2 | 2 | 82 | 2.25 | 2017-10-23 | Sprint 2
Product 5 | Story 4 | 2017-07-25 | Requirement | 2017-07-29 | 2017-08-06 | 8 | 4 | DCUT | 2017-08-08 | 2017-08-20 | 12 | 2 | DeployDev | 2017-08-20 | 2017-08-23 | 3 | 0 | InegrationTest | 2017-08-23 | 2017-08-25 | 2 | 0 | DeployQA | 2017-08-26 | 2017-08-27 | 1 | 1 | FunctionTest | 2017-08-27 | 2017-09-24 | 28 | 0 | DeployNFR | 2017-09-25 | 2017-09-30 | 5 | 1 | TestNFR | 2017-10-02 | 2017-10-18 | 16 | 2 | TollGate | 2017-10-19 | 2017-10-30 | 11 | 1 | DeployProd | 2017-11-01 | 2017-11-04 | 3 | 2 | 98 | 3 | 2017-11-04 | Sprint 1
Product 5 | Story 6 | 2017-07-26 | Requirement | 2017-07-30 | 2017-08-09 | 10 | 4 | DCUT | 2017-08-11 | 2017-08-23 | 12 | 2 | DeployDev | 2017-08-23 | 2017-08-25 | 2 | 0 | InegrationTest | 2017-08-28 | 2017-09-01 | 4 | 3 | DeployQA | 2017-09-02 | 2017-09-02 | 0 | 1 | FunctionTest | 2017-09-02 | 2017-09-28 | 26 | 0 | DeployNFR | 2017-09-29 | 2017-10-06 | 7 | 1 | TestNFR | 2017-10-08 | 2017-10-20 | 12 | 2 | TollGate | 2017-10-22 | 2017-10-31 | 9 | 2 | DeployProd | 2017-11-03 | 2017-11-06 | 3 | 3 | 99 | 3 | 2017-11-06 | Sprint 1
Product 5 | Story 2 | 2017-07-31 | Requirement | 2017-08-01 | 2017-08-10 | 9 | 1 | DCUT | 2017-08-11 | 2017-08-22 | 11 | 1 | DeployDev | 2017-08-22 | 2017-08-23 | 1 | 0 | InegrationTest | 2017-08-24 | 2017-08-30 | 6 | 1 | DeployQA | 2017-08-31 | 2017-08-31 | 0 | 1 | FunctionTest | 2017-08-31 | 2017-09-25 | 25 | 0 | DeployNFR | 2017-09-26 | 2017-10-01 | 5 | 1 | TestNFR | 2017-10-05 | 2017-10-22 | 17 | 4 | TollGate | 2017-10-24 | 2017-11-03 | 10 | 2 | DeployProd | 2017-11-07 | 2017-11-09 | 2 | 4 | 100 | 2 | 2017-11-09 | Sprint 1 | 99
Product 6 | Story 11 | 2017-06-06 | Requirement | 2017-06-07 | 2017-06-20 | 13 | 1 | DCUT | 2017-06-21 | 2017-07-01 | 10 | 1 | DeployDev | 2017-07-01 | 2017-07-03 | 2 | 0 | InegrationTest | 2017-07-05 | 2017-07-09 | 4 | 2 | DeployQA | 2017-07-11 | 2017-07-13 | 2 | 2 | FunctionTest | 2017-07-15 | 2017-08-03 | 19 | 2 | DeployNFR | 2017-08-03 | 2017-08-10 | 7 | 0 | TestNFR | 2017-08-14 | 2017-08-22 | 8 | 4 | TollGate | 2017-08-24 | 2017-08-28 | 4 | 2 | DeployProd | 2017-09-02 | 2017-09-08 | 6 | 5 | 93 | 4.25 | 2017-09-08 | Sprint 5
Product 6 | Story 13 | 2017-06-09 | Requirement | 2017-06-12 | 2017-06-23 | 11 | 3 | DCUT | 2017-06-25 | 2017-07-07 | 12 | 2 | DeployDev | 2017-07-08 | 2017-07-10 | 2 | 1 | InegrationTest | 2017-07-10 | 2017-07-12 | 2 | 0 | DeployQA | 2017-07-14 | 2017-07-15 | 1 | 2 | FunctionTest | 2017-07-15 | 2017-08-05 | 21 | 0 | DeployNFR | 2017-08-05 | 2017-08-08 | 3 | 0 | TestNFR | 2017-08-11 | 2017-08-20 | 9 | 3 | TollGate | 2017-08-24 | 2017-08-26 | 2 | 4 | DeployProd | 2017-08-31 | 2017-09-05 | 5 | 5 | 85 | 2.75 | 2017-09-05 | Sprint 5
Product 6 | Story 14 | 2017-06-23 | Requirement | 2017-06-25 | 2017-07-07 | 12 | 2 | DCUT | 2017-07-08 | 2017-07-20 | 12 | 1 | DeployDev | 2017-07-20 | 2017-07-20 | 0 | 0 | InegrationTest | 2017-07-22 | 2017-07-26 | 4 | 2 | DeployQA | 2017-07-27 | 2017-07-28 | 1 | 1 | FunctionTest | 2017-07-28 | 2017-08-14 | 17 | 0 | DeployNFR | 2017-08-16 | 2017-08-20 | 4 | 2 | TestNFR | 2017-08-24 | 2017-09-03 | 10 | 4 | TollGate | 2017-09-05 | 2017-09-08 | 3 | 2 | DeployProd | 2017-09-14 | 2017-09-18 | 4 | 6 | 85 | 2.25 | 2017-09-18 | Sprint 5
Product 6 | Story 12 | 2017-07-05 | Requirement | 2017-07-07 | 2017-07-18 | 11 | 2 | DCUT | 2017-07-20 | 2017-07-31 | 11 | 2 | DeployDev | 2017-07-31 | 2017-08-01 | 1 | 0 | InegrationTest | 2017-08-01 | 2017-08-04 | 3 | 0 | DeployQA | 2017-08-05 | 2017-08-06 | 1 | 1 | FunctionTest | 2017-08-07 | 2017-08-22 | 15 | 1 | DeployNFR | 2017-08-24 | 2017-08-28 | 4 | 2 | TestNFR | 2017-08-30 | 2017-09-08 | 9 | 2 | TollGate | 2017-09-09 | 2017-09-12 | 3 | 1 | DeployProd | 2017-09-16 | 2017-09-20 | 4 | 4 | 75 | 2.5 | 2017-09-20 | Sprint 4
Product 6 | Story 10 | 2017-07-05 | Requirement | 2017-07-07 | 2017-07-18 | 11 | 2 | DCUT | 2017-07-20 | 2017-07-30 | 10 | 2 | DeployDev | 2017-07-31 | 2017-08-01 | 1 | 1 | InegrationTest | 2017-08-01 | 2017-08-04 | 3 | 0 | DeployQA | 2017-08-05 | 2017-08-06 | 1 | 1 | FunctionTest | 2017-08-06 | 2017-08-20 | 14 | 0 | DeployNFR | 2017-08-21 | 2017-08-25 | 4 | 1 | TestNFR | 2017-08-28 | 2017-09-04 | 7 | 3 | TollGate | 2017-09-09 | 2017-09-12 | 3 | 5 | DeployProd | 2017-09-18 | 2017-09-23 | 5 | 6 | 78 | 2.75 | 2017-09-23 | Sprint 4
Product 6 | Story 9 | 2017-07-20 | Requirement | 2017-07-23 | 2017-08-02 | 10 | 3 | DCUT | 2017-08-05 | 2017-08-15 | 10 | 3 | DeployDev | 2017-08-15 | 2017-08-17 | 2 | 0 | InegrationTest | 2017-08-17 | 2017-08-19 | 2 | 0 | DeployQA | 2017-08-21 | 2017-08-22 | 1 | 2 | FunctionTest | 2017-08-23 | 2017-09-04 | 12 | 1 | DeployNFR | 2017-09-04 | 2017-09-09 | 5 | 0 | TestNFR | 2017-09-11 | 2017-09-17 | 6 | 2 | TollGate | 2017-09-21 | 2017-09-23 | 2 | 4 | DeployProd | 2017-09-27 | 2017-10-03 | 6 | 4 | 72 | 3.5 | 2017-10-03 | Sprint 4
Product 6 | Story 15 | 2017-06-23 | Requirement | 2017-06-24 | 2017-07-03 | 9 | 1 | DCUT | 2017-07-03 | 2017-07-14 | 11 | 0 | DeployDev | 2017-07-14 | 2017-07-14 | 0 | 0 | InegrationTest | 2017-07-15 | 2017-07-20 | 5 | 1 | DeployQA | 2017-07-22 | 2017-07-23 | 1 | 2 | FunctionTest | 2017-07-24 | 2017-08-04 | 11 | 1 | DeployNFR | 2017-08-05 | 2017-08-09 | 4 | 1 | TestNFR | 2017-08-09 | 2017-08-16 | 7 | 0 | TollGate | 2017-08-19 | 2017-08-24 | 5 | 3 | DeployProd | 2017-08-29 | 2017-09-03 | 5 | 5 | 71 | 2.5 | 2017-09-03 | Sprint 3
Product 6 | Story 5 | 2017-07-23 | Requirement | 2017-07-24 | 2017-08-02 | 9 | 1 | DCUT | 2017-08-04 | 2017-08-13 | 9 | 2 | DeployDev | 2017-08-13 | 2017-08-15 | 2 | 0 | InegrationTest | 2017-08-16 | 2017-08-19 | 3 | 1 | DeployQA | 2017-08-21 | 2017-08-23 | 2 | 2 | FunctionTest | 2017-08-23 | 2017-09-03 | 11 | 0 | DeployNFR | 2017-09-04 | 2017-09-08 | 4 | 1 | TestNFR | 2017-09-10 | 2017-09-22 | 12 | 2 | TollGate | 2017-09-25 | 2017-09-27 | 2 | 3 | DeployProd | 2017-10-03 | 2017-10-08 | 5 | 6 | 76 | 3.25 | 2017-10-08 | Sprint 3
Product 6 | Story 8 | 2017-07-18 | Requirement | 2017-07-20 | 2017-07-30 | 10 | 2 | DCUT | 2017-08-01 | 2017-08-13 | 12 | 2 | DeployDev | 2017-08-14 | 2017-08-15 | 1 | 1 | InegrationTest | 2017-08-16 | 2017-08-19 | 3 | 1 | DeployQA | 2017-08-20 | 2017-08-21 | 1 | 1 | FunctionTest | 2017-08-21 | 2017-08-31 | 10 | 0 | DeployNFR | 2017-09-01 | 2017-09-07 | 6 | 1 | TestNFR | 2017-09-08 | 2017-09-17 | 9 | 1 | TollGate | 2017-09-19 | 2017-09-24 | 5 | 2 | DeployProd | 2017-09-29 | 2017-10-06 | 7 | 5 | 78 | 3.75 | 2017-10-06 | Sprint 3
Product 6 | Story 4 | 2017-08-06 | Requirement | 2017-08-08 | 2017-08-17 | 9 | 2 | DCUT | 2017-08-19 | 2017-08-30 | 11 | 2 | DeployDev | 2017-08-31 | 2017-09-01 | 1 | 1 | InegrationTest | 2017-09-01 | 2017-09-05 | 4 | 0 | DeployQA | 2017-09-06 | 2017-09-07 | 1 | 1 | FunctionTest | 2017-09-09 | 2017-09-21 | 12 | 2 | DeployNFR | 2017-09-22 | 2017-09-25 | 3 | 1 | TestNFR | 2017-09-26 | 2017-10-07 | 11 | 1 | TollGate | 2017-10-09 | 2017-10-12 | 3 | 2 | DeployProd | 2017-10-17 | 2017-10-20 | 3 | 5 | 73 | 2 | 2017-10-20 | Sprint 2
Product 6 | Story 2 | 2017-08-14 | Requirement | 2017-08-16 | 2017-08-24 | 8 | 2 | DCUT | 2017-08-26 | 2017-09-05 | 10 | 2 | DeployDev | 2017-09-05 | 2017-09-07 | 2 | 0 | InegrationTest | 2017-09-07 | 2017-09-10 | 3 | 0 | DeployQA | 2017-09-11 | 2017-09-12 | 1 | 1 | FunctionTest | 2017-09-12 | 2017-09-20 | 8 | 0 | DeployNFR | 2017-09-20 | 2017-09-25 | 5 | 0 | TestNFR | 2017-09-27 | 2017-10-06 | 9 | 2 | TollGate | 2017-10-08 | 2017-10-09 | 1 | 2 | DeployProd | 2017-10-13 | 2017-10-19 | 6 | 4 | 64 | 3.5 | 2017-10-19 | Sprint 2
Product 6 | Story 6 | 2017-08-16 | Requirement | 2017-08-18 | 2017-08-25 | 7 | 2 | DCUT | 2017-08-27 | 2017-09-06 | 10 | 2 | DeployDev | 2017-09-07 | 2017-09-08 | 1 | 1 | InegrationTest | 2017-09-08 | 2017-09-10 | 2 | 0 | DeployQA | 2017-09-11 | 2017-09-12 | 1 | 1 | FunctionTest | 2017-09-13 | 2017-09-22 | 9 | 1 | DeployNFR | 2017-09-23 | 2017-09-28 | 5 | 1 | TestNFR | 2017-10-01 | 2017-10-09 | 8 | 3 | TollGate | 2017-10-11 | 2017-10-15 | 4 | 2 | DeployProd | 2017-10-19 | 2017-10-23 | 4 | 4 | 66 | 2.75 | 2017-10-23 | Sprint 2
Product 6 | Story 3 | 2017-08-26 | Requirement | 2017-08-29 | 2017-09-04 | 6 | 3 | DCUT | 2017-09-05 | 2017-09-16 | 11 | 1 | DeployDev | 2017-09-16 | 2017-09-17 | 1 | 0 | InegrationTest | 2017-09-18 | 2017-09-20 | 2 | 1 | DeployQA | 2017-09-21 | 2017-09-23 | 2 | 1 | FunctionTest | 2017-09-23 | 2017-10-01 | 8 | 0 | DeployNFR | 2017-10-01 | 2017-10-07 | 6 | 0 | TestNFR | 2017-10-10 | 2017-10-20 | 10 | 3 | TollGate | 2017-10-24 | 2017-10-26 | 2 | 4 | DeployProd | 2017-10-31 | 2017-11-04 | 4 | 5 | 67 | 3.25 | 2017-11-04 | Sprint 1
Product 6 | Story 7 | 2017-09-01 | Requirement | 2017-09-02 | 2017-09-08 | 6 | 1 | DCUT | 2017-09-09 | 2017-09-18 | 9 | 1 | DeployDev | 2017-09-18 | 2017-09-20 | 2 | 0 | InegrationTest | 2017-09-20 | 2017-09-24 | 4 | 0 | DeployQA | 2017-09-26 | 2017-09-27 | 1 | 2 | FunctionTest | 2017-09-27 | 2017-10-04 | 7 | 0 | DeployNFR | 2017-10-05 | 2017-10-09 | 4 | 1 | TestNFR | 2017-10-13 | 2017-10-20 | 7 | 4 | TollGate | 2017-10-23 | 2017-10-26 | 3 | 3 | DeployProd | 2017-11-01 | 2017-11-06 | 5 | 6 | 65 | 3 | 2017-11-06 | Sprint 1
Product 6 | Story 1 | 2017-09-07 | Requirement | 2017-09-09 | 2017-09-14 | 5 | 2 | DCUT | 2017-09-15 | 2017-09-23 | 8 | 1 | DeployDev | 2017-09-23 | 2017-09-24 | 1 | 0 | InegrationTest | 2017-09-24 | 2017-09-27 | 3 | 0 | DeployQA | 2017-09-28 | 2017-09-29 | 1 | 1 | FunctionTest | 2017-09-30 | 2017-10-09 | 9 | 1 | DeployNFR | 2017-10-10 | 2017-10-14 | 4 | 1 | TestNFR | 2017-10-17 | 2017-10-25 | 8 | 3 | TollGate | 2017-10-28 | 2017-10-30 | 2 | 3 | DeployProd | 2017-11-04 | 2017-11-09 | 5 | 5 | 61 | 2.75 | 2017-11-09 | Sprint 1 | 64.3333
Product 4 |  |  | Requirement | 2017-06-30 22:00 | 2017-07-11 04:00 | 10.25 | 2.3333 | DCUT | 2017-07-13 12:00 | 2017-07-27 18:00 | 14.25 | 2.75 | DeployDev | 2017-07-30 12:00 | 2017-08-02 22:00 | 3.4167 | 2.75 | InegrationTest | 2017-08-05 16:00 | 2017-08-09 10:00 | 3.75 | 2.9167 | DeployQA | 2017-08-12 08:00 | 2017-08-16 04:00 | 3.8333 | 3.5 | FunctionTest | 2017-08-19 16:00 | 2017-09-07 12:00 | 18.8333 | 2.25 | DeployNFR | 2017-09-09 18:00 | 2017-09-14 | 4.25 | 4.4167 | TestNFR | 2017-09-18 10:00 | 2017-09-28 16:00 | 10.25 | 3.0833 | TollGate | 2017-10-01 18:00 | 2017-10-03 18:00 | 2 | 3.9167 | DeployProd | 2017-10-07 16:00 | 2017-10-13 12:00 | 5.8333
Product 5 |  |  | Requirement | 2017-07-11 22:24 | 2017-07-19 01:36 | 7.1333 | 1.6667 | DCUT | 2017-07-20 17:36 | 2017-07-31 09:36 | 10.6667 | 0 | DeployDev | 2017-07-31 09:36 | 2017-08-01 22:24 | 1.5333 | 0.93333 | InegrationTest | 2017-08-02 20:48 | 2017-08-06 03:12 | 3.2667 | 0.8 | DeployQA | 2017-08-06 22:24 | 2017-08-07 20:48 | 0.93333 | 0.066667 | FunctionTest | 2017-08-07 22:24 | 2017-08-29 03:12 | 21.2 | 1.2 | DeployNFR | 2017-08-30 08:00 | 2017-09-03 14:24 | 4.2667 | 2.5333 | TestNFR | 2017-09-06 03:12 | 2017-09-17 17:36 | 11.6 | 2.5333 | TollGate | 2017-09-20 06:24 | 2017-09-30 19:12 | 10.5333 | 2.5333 | DeployProd | 2017-10-03 08:00 | 2017-10-05 20:48 | 2.5333
Product 6 |  |  | Requirement | 2017-07-23 22:24 | 2017-08-02 01:36 | 9.1333 | 1.6 | DCUT | 2017-08-03 16:00 | 2017-08-14 01:36 | 10.4 | 0.33333 | DeployDev | 2017-08-14 09:36 | 2017-08-15 16:00 | 1.2667 | 0.53333 | InegrationTest | 2017-08-16 04:48 | 2017-08-19 08:00 | 3.1333 | 1.4 | DeployQA | 2017-08-20 17:36 | 2017-08-21 22:24 | 1.2 | 0.6 | FunctionTest | 2017-08-22 12:48 | 2017-09-03 17:36 | 12.2 | 0.8 | DeployNFR | 2017-09-04 12:48 | 2017-09-09 01:36 | 4.5333 | 2.4667 | TestNFR | 2017-09-11 12:48 | 2017-09-20 04:48 | 8.6667 | 2.8 | TollGate | 2017-09-23 | 2017-09-25 22:24 | 2.9333 | 5 | DeployProd | 2017-09-30 22:24 | 2017-10-05 20:48 | 4.9333

## Level 2
Row Labels | Average of Velocity | Sum of Deployment/ sprint | Sum of LoC changed/ sprint | Sum of Failed Deployment / sprint | Max of Ticket Volume | Max of Technical Debt (TD) | Max of # of items on Hold | Average of Lead Time | Total of Avg Deployment time
Product 4 | 93.25 | 114 | 1421 | 22 | 13 | 91 | 13 | 126.5833 | 52
Story 1 | 93.25 | 114 | 1421 | 22 | 13 | 91 | 13 | 126.5833 | 52
Product 5 | 90.7333 | 136 | 1680 | 23 | 8 | 66 | 13 | 88.9333 | 32.75
Story 1 | 92.2222 | 83 | 1009 | 13 | 8 | 66 | 13 | 88 | 20.25
Story 2 | 88.5 | 53 | 671 | 10 | 7 | 50 | 12 | 90.3333 | 12.5
Grand Total | 91.8519 | 250 | 3101 | 45 | 13 | 91 | 13 | 105.6667 | 84.75

## Level2_Data
Product Name | Work Item | Start End Date | Date_Velocity | Velocity | Date_Deployment/ sprint | Deployment/ sprint | Date_LoC changed/ sprint | LoC changed/ sprint | Date_Failed Deployment / sprint | Failed Deployment / sprint | Date_Ticket Volume | Ticket Volume | Date_Technical Debt (TD) | Technical Debt (TD) | Date_# of items on Hold | # of items on Hold | Lead Time (roll up from L3) | Avg Deployment time
Product 4 | Story 1 | AnyDate | 2017-09-18 | 92 | 2017-09-18 | 13 | 2017-09-18 | 102 | 2017-09-18 | 2 | 2017-09-18 | 13 | 2017-09-18 | 56 | 2017-09-18 | 8 | 109 | 5.75
Product 4 | Story 1 | AnyDate | 2017-09-20 | 85 | 2017-09-20 | 12 | 2017-09-20 | 87 | 2017-09-20 | 2 | 2017-09-20 | 9 | 2017-09-20 | 36 | 2017-09-20 | 12 | 115 | 6.25
Product 4 | Story 1 | AnyDate | 2017-09-23 | 84 | 2017-09-23 | 12 | 2017-09-23 | 111 | 2017-09-23 | 3 | 2017-09-23 | 12 | 2017-09-23 | 47 | 2017-09-23 | 9 | 106 | 5.25
Product 4 | Story 1 | AnyDate | 2017-10-03 | 90 | 2017-10-03 | 11 | 2017-10-03 | 130 | 2017-10-03 | 3 | 2017-10-03 | 13 | 2017-10-03 | 54 | 2017-10-03 | 13 | 105 | 5.25
Product 4 | Story 1 | AnyDate | 2017-10-06 | 92 | 2017-10-06 | 13 | 2017-10-06 | 102 | 2017-10-06 | 3 | 2017-10-06 | 11 | 2017-10-06 | 42 | 2017-10-06 | 12 | 96 | 4.5
Product 4 | Story 1 | AnyDate | 2017-10-08 | 89 | 2017-10-08 | 11 | 2017-10-08 | 91 | 2017-10-08 | 2 | 2017-10-08 | 10 | 2017-10-08 | 38 | 2017-10-08 | 13 | 94 | 5
Product 4 | Story 1 | AnyDate | 2017-10-19 | 90 | 2017-10-19 | 11 | 2017-10-19 | 109 | 2017-10-19 | 3 | 2017-10-19 | 9 | 2017-10-19 | 43 | 2017-10-19 | 10 | 94 | 3.75
Product 4 | Story 1 | AnyDate | 2017-10-20 | 92 | 2017-10-20 | 12 | 2017-10-20 | 104 | 2017-10-20 | 3 | 2017-10-20 | 9 | 2017-10-20 | 41 | 2017-10-20 | 5 | 103 | 3.75
Product 4 | Story 1 | AnyDate | 2017-10-23 | 98 | 2017-10-23 | 14 | 2017-10-23 | 111 | 2017-10-23 | 2 | 2017-10-23 | 11 | 2017-10-23 | 47 | 2017-10-23 | 6 | 94 | 3.5
Product 4 | Story 1 | AnyDate | 2017-11-04 | 86 | 2017-11-04 | 12 | 2017-11-04 | 107 | 2017-11-04 | 2 | 2017-11-04 | 9 | 2017-11-04 | 53 | 2017-11-04 | 10 | 113 | 3.25
Product 4 | Story 1 | AnyDate | 2017-11-06 | 98 | 2017-11-06 | 12 | 2017-11-06 | 99 | 2017-11-06 | 3 | 2017-11-06 | 11 | 2017-11-06 | 41 | 2017-11-06 | 10 | 112 | 3.75
Product 4 | Story 1 | AnyDate | 2017-11-09 | 95 | 2017-11-09 | 12 | 2017-11-09 | 134 | 2017-11-09 | 3 | 2017-11-09 | 14 | 2017-11-09 | 64 | 2017-11-09 | 12 | 114 | 2
Product 5 | Story 1 | AnyDate | 2017-09-03 | 90 | 2017-09-03 | 11 | 2017-09-03 | 125 | 2017-09-03 | 3 | 2017-09-03 | 13 | 2017-09-03 | 73 | 2017-09-03 | 12 | 82 | 2.75
Product 5 | Story 1 | AnyDate | 2017-09-05 | 92 | 2017-09-05 | 13 | 2017-09-05 | 117 | 2017-09-05 | 2 | 2017-09-05 | 11 | 2017-09-05 | 73 | 2017-09-05 | 11 | 77 | 1.75
Product 5 | Story 1 | AnyDate | 2017-09-08 | 85 | 2017-09-08 | 12 | 2017-09-08 | 116 | 2017-09-08 | 3 | 2017-09-08 | 13 | 2017-09-08 | 74 | 2017-09-08 | 9 | 84 | 2.25
Product 5 | Story 2 | AnyDate | 2017-09-18 | 84 | 2017-09-18 | 12 | 2017-09-18 | 84 | 2017-09-18 | 3 | 2017-09-18 | 9 | 2017-09-18 | 51 | 2017-09-18 | 12 | 81 | 2.25
Product 5 | Story 2 | AnyDate | 2017-09-20 | 90 | 2017-09-20 | 12 | 2017-09-20 | 95 | 2017-09-20 | 3 | 2017-09-20 | 8 | 2017-09-20 | 54 | 2017-09-20 | 6 | 85 | 2.75
Product 5 | Story 2 | AnyDate | 2017-09-23 | 92 | 2017-09-23 | 12 | 2017-09-23 | 136 | 2017-09-23 | 2 | 2017-09-23 | 14 | 2017-09-23 | 99 | 2017-09-23 | 12 | 83 | 1.5
Product 5 | Story 1 | AnyDate | 2017-10-03 | 89 | 2017-10-03 | 11 | 2017-10-03 | 91 | 2017-10-03 | 3 | 2017-10-03 | 9 | 2017-10-03 | 50 | 2017-10-03 | 11 | 84 | 2.25
Product 5 | Story 1 | AnyDate | 2017-10-06 | 90 | 2017-10-06 | 12 | 2017-10-06 | 96 | 2017-10-06 | 3 | 2017-10-06 | 9 | 2017-10-06 | 62 | 2017-10-06 | 5 | 85 | 2.5
Product 5 | Story 1 | AnyDate | 2017-10-08 | 95 | 2017-10-08 | 13 | 2017-10-08 | 132 | 2017-10-08 | 3 | 2017-10-08 | 14 | 2017-10-08 | 76 | 2017-10-08 | 7 | 84 | 1.5
Product 5 | Story 1 | AnyDate | 2017-10-19 | 99 | 2017-10-19 | 13 | 2017-10-19 | 127 | 2017-10-19 | 3 | 2017-10-19 | 13 | 2017-10-19 | 89 | 2017-10-19 | 12 | 80 | 2.25
Product 5 | Story 1 | AnyDate | 2017-10-20 | 100 | 2017-10-20 | 13 | 2017-10-20 | 126 | 2017-10-20 | 3 | 2017-10-20 | 16 | 2017-10-20 | 83 | 2017-10-20 | 15 | 85 | 2.75
Product 5 | Story 1 | AnyDate | 2017-10-23 | 90 | 2017-10-23 | 11 | 2017-10-23 | 108 | 2017-10-23 | 2 | 2017-10-23 | 10 | 2017-10-23 | 76 | 2017-10-23 | 13 | 82 | 2.25
Product 5 | Story 2 | AnyDate | 2017-11-04 | 92 | 2017-11-04 | 12 | 2017-11-04 | 123 | 2017-11-04 | 2 | 2017-11-04 | 12 | 2017-11-04 | 36 | 2017-11-04 | 6 | 98 | 3
Product 5 | Story 2 | AnyDate | 2017-11-06 | 89 | 2017-11-06 | 12 | 2017-11-06 | 103 | 2017-11-06 | 2 | 2017-11-06 | 12 | 2017-11-06 | 55 | 2017-11-06 | 5 | 99 | 3
Product 5 | Story 2 | AnyDate | 2017-11-09 | 84 | 2017-11-09 | 11 | 2017-11-09 | 104 | 2017-11-09 | 3 | 2017-11-09 | 10 | 2017-11-09 | 45 | 2017-11-09 | 5 | 100 | 2
Product 6 | AnyStory | AnyDate | 2017-09-03 | 90 | 2017-09-03 | 13 | 2017-09-03 | 123 | 2017-09-03 | 2 | 2017-09-03 | 12 | 2017-09-03 | 88 | 2017-09-03 | 5 | 93 | 4.25
Product 6 | AnyStory | AnyDate | 2017-09-05 | 92 | 2017-09-05 | 13 | 2017-09-05 | 113 | 2017-09-05 | 3 | 2017-09-05 | 14 | 2017-09-05 | 75 | 2017-09-05 | 6 | 85 | 2.75
Product 6 | AnyStory | AnyDate | 2017-09-08 | 85 | 2017-09-08 | 11 | 2017-09-08 | 119 | 2017-09-08 | 3 | 2017-09-08 | 10 | 2017-09-08 | 67 | 2017-09-08 | 5 | 85 | 2.25
Product 6 | AnyStory | AnyDate | 2017-09-18 | 84 | 2017-09-18 | 12 | 2017-09-18 | 103 | 2017-09-18 | 2 | 2017-09-18 | 11 | 2017-09-18 | 57 | 2017-09-18 | 5 | 75 | 2.5
Product 6 | AnyStory | AnyDate | 2017-09-20 | 90 | 2017-09-20 | 13 | 2017-09-20 | 107 | 2017-09-20 | 3 | 2017-09-20 | 13 | 2017-09-20 | 69 | 2017-09-20 | 10 | 78 | 2.75
Product 6 | AnyStory | AnyDate | 2017-09-23 | 92 | 2017-09-23 | 13 | 2017-09-23 | 112 | 2017-09-23 | 2 | 2017-09-23 | 12 | 2017-09-23 | 67 | 2017-09-23 | 11 | 72 | 3.5
Product 6 | AnyStory | AnyDate | 2017-10-03 | 89 | 2017-10-03 | 11 | 2017-10-03 | 116 | 2017-10-03 | 3 | 2017-10-03 | 11 | 2017-10-03 | 74 | 2017-10-03 | 6 | 71 | 2.5
Product 6 | AnyStory | AnyDate | 2017-10-06 | 90 | 2017-10-06 | 13 | 2017-10-06 | 133 | 2017-10-06 | 3 | 2017-10-06 | 15 | 2017-10-06 | 72 | 2017-10-06 | 9 | 76 | 3.25
Product 6 | AnyStory | AnyDate | 2017-10-08 | 95 | 2017-10-08 | 14 | 2017-10-08 | 102 | 2017-10-08 | 4 | 2017-10-08 | 14 | 2017-10-08 | 59 | 2017-10-08 | 11 | 78 | 3.75
Product 6 | AnyStory | AnyDate | 2017-10-19 | 99 | 2017-10-19 | 12 | 2017-10-19 | 110 | 2017-10-19 | 2 | 2017-10-19 | 12 | 2017-10-19 | 87 | 2017-10-19 | 10 | 73 | 2
Product 6 | AnyStory | AnyDate | 2017-10-20 | 100 | 2017-10-20 | 12 | 2017-10-20 | 145 | 2017-10-20 | 3 | 2017-10-20 | 13 | 2017-10-20 | 112 | 2017-10-20 | 5 | 64 | 3.5
Product 6 | AnyStory | AnyDate | 2017-10-23 | 100 | 2017-10-23 | 15 | 2017-10-23 | 109 | 2017-10-23 | 4 | 2017-10-23 | 12 | 2017-10-23 | 78 | 2017-10-23 | 5 | 66 | 2.75
Product 6 | AnyStory | AnyDate | 2017-11-04 | 120 | 2017-11-04 | 18 | 2017-11-04 | 136 | 2017-11-04 | 2 | 2017-11-04 | 11 | 2017-11-04 | 113 | 2017-11-04 | 10 | 67 | 3.25
Product 6 | AnyStory | AnyDate | 2017-11-06 | 130 | 2017-11-06 | 19 | 2017-11-06 | 133 | 2017-11-06 | 2 | 2017-11-06 | 15 | 2017-11-06 | 138 | 2017-11-06 | 12 | 65 | 3
Product 6 | AnyStory | AnyDate | 2017-11-09 | 128 | 2017-11-09 | 16 | 2017-11-09 | 136 | 2017-11-09 | 4 | 2017-11-09 | 12 | 2017-11-09 | 130 | 2017-11-09 | 10 | 61 | 2.75
Product 4 | Current Sprint |  |  | 93 |  | 36 |  | 340 |  | 8 |  | 14 |  | 64 |  | 12 |  | 3
Product 4 | Current Sprint -1 |  |  | 93.33 |  | 37 |  | 324 |  | 8 |  | 11 |  | 47 |  | 10 |  | 3.67
Product 4 | Current Sprint -2 |  |  | 90.33 |  | 35 |  | 323 |  | 8 |  | 13 |  | 54 |  | 13 |  | 4.92
Product 4 | Current Sprint -3 |  |  | 87 |  | 37 |  | 300 |  | 7 |  | 13 |  | 56 |  | 12 |  | 5.75
Product 4 | Average (Prev 3 Sprint) |  |  | 90.22 |  | 36.33 |  | 315.67 |  | 7.67 |  | 12.33 |  | 52.33 |  | 11.67 |  | 4.78
Product 4 | Difference |  |  | 2.78 |  | -0.33 |  | 24.33 |  | 0.33 |  | 1.67 |  | 11.67 |  | 0.33 |  | -1.78
Product 4 | Difference in % |  |  | 3.08 |  | -0.91 |  | 7.71 |  | 4.3 |  | 13.54 |  | 22.3 |  | 2.83 |  | -37.24
Product 4 | Difference in % Range (-10 to +10) |  |  | TRUE |  | TRUE |  | TRUE |  | TRUE |  | FALSE |  | FALSE |  | TRUE |  | FALSE
Product 4 | Current Sprint < Average |  |  | FALSE |  | TRUE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | TRUE
Product 4 | Trend Rule |  |  | 1 |  | 1 |  | 1 |  | 2 |  | 2 |  | 2 |  | 2 |  | 1
Product 4 | Arrow |  |  | up-grey |  | down-grey |  | up-grey |  | down-green |  | up-red |  | up-red |  | doen-green |  | down-green
Product 5 | Current Sprint |  |  | 88.33 |  | 35 |  | 330 |  | 7 |  | 12 |  | 55 |  | 6 |  | 2.67
Product 5 | Current Sprint -1 |  |  | 96.33 |  | 37 |  | 361 |  | 8 |  | 16 |  | 89 |  | 15 |  | 2.42
Product 5 | Current Sprint -2 |  |  | 91.33 |  | 36 |  | 319 |  | 9 |  | 14 |  | 76 |  | 11 |  | 2.08
Product 5 | Current Sprint -3 |  |  | 88.67 |  | 36 |  | 315 |  | 8 |  | 14 |  | 99 |  | 12 |  | 2.17
Product 5 | Average (Prev 3 Sprint) |  |  | 92.11 |  | 36.33 |  | 331.67 |  | 8.33 |  | 14.67 |  | 88 |  | 12.67 |  | 2.22
Product 5 | Difference |  |  | -3.78 |  | -1.33 |  | -1.67 |  | -1.33 |  | -2.67 |  | -33 |  | -6.67 |  | 0.45
Product 5 | Difference in % |  |  | -4.1 |  | -3.66 |  | -0.5 |  | -15.97 |  | -18.2 |  | -37.5 |  | -52.64 |  | 20.27
Product 5 | Difference in % Range (-10 to +10) |  |  | TRUE |  | TRUE |  | TRUE |  | FALSE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Product 5 | Current Sprint < Average |  |  | TRUE |  | TRUE |  | TRUE |  | TRUE |  | TRUE |  | TRUE |  | TRUE |  | FALSE
Product 5 | Trend Rule |  |  | 1 |  | 2 |  | 1 |  | 2 |  | 2 |  | 2 |  | 2 |  | 1
Product 5 | Arrow |  |  | down-grey |  | up-grey |  | up-grey |  | up-grey |  | up-red |  | down-green |  | up-red |  | down-red
Product 6 | Current Sprint |  |  | 126 |  | 53 |  | 405 |  | 8 |  | 15 |  | 138 |  | 12 |  | 3
Product 6 | Current Sprint -1 |  |  | 99.67 |  | 39 |  | 364 |  | 9 |  | 13 |  | 112 |  | 10 |  | 2.75
Product 6 | Current Sprint -2 |  |  | 91.33 |  | 38 |  | 351 |  | 10 |  | 15 |  | 74 |  | 11 |  | 3.17
Product 6 | Current Sprint -3 |  |  | 88.67 |  | 38 |  | 322 |  | 7 |  | 13 |  | 69 |  | 11 |  | 2.92
Product 6 | Average (Prev 3 Sprint) |  |  | 93.22 |  | 38.33 |  | 345.67 |  | 8.67 |  | 13.67 |  | 85 |  | 10.67 |  | 2.95
Product 6 | Difference |  |  | 32.78 |  | 14.67 |  | 59.33 |  | -0.67 |  | 1.33 |  | 53 |  | 1.33 |  | 0.05
Product 6 | Difference in % |  |  | 35.16 |  | 38.27 |  | 17.16 |  | -7.73 |  | 9.73 |  | 62.35 |  | 12.46 |  | 1.69
Product 6 | Difference in % Range (-10 to +10) |  |  | FALSE |  | FALSE |  | FALSE |  | TRUE |  | TRUE |  | FALSE |  | FALSE |  | TRUE
Product 6 | Current Sprint < Average |  |  | FALSE |  | FALSE |  | FALSE |  | TRUE |  | FALSE |  | FALSE |  | FALSE |  | FALSE
Product 6 | Trend Rule |  |  | 1 |  | 2 |  | 1 |  | 2 |  | 2 |  | 2 |  | 2 |  | 1
Product 6 | Arrow |  |  | up-green |  | up-green |  | down-grey |  | up-red |  | up-red |  | up-red |  | up-red |  | down-red
|  | Today | 2017-11-09
| Current Sprint | Week 1 | 2017-11-08
|  | Week 2 | 2017-11-01
| Current Sprint -1 | Week 3 | 2017-10-25
|  | Week 4 | 2017-10-18
| Current Sprint -2 | Week 5 | 2017-10-11
|  | Week 6 | 2017-10-04
| Current Sprint -3 | Week 7 | 2017-09-27
|  | Week 8 | 2017-09-20
|  | Week 9 | 2017-09-13
Formulas:
Date_Velocity = [Date_Velocity, row above]-1

## Sheet1
Start Date | 2017-11-09
end Date | 2017-09-14
today | 2017-11-08
Week 1 | 2017-11-02
Week 2 | 2017-10-26
Week 3 | 2017-10-19
Week 4 | 2017-10-12
Week 5 | 2017-10-05
Week 6 | 2017-09-28
Week 7 | 2017-09-21
Week 8 | 2017-09-14